|  | Example Name | ID & Version | Phase | Creation |
| --- | --- | --- | --- | --- |
|  | Content Project Brief | cpb-pln-xmpl-01 | Planning | March 2015 |
| Project | Video | Job # | 8000-14 |
| Content Strategy Lead | Rhoda Carr | Account Manager | Lou Alcindor |
| Project Manager | Sandy Beach | Creative Director | Crispin Porter |
| Business Owner | Chanda Lear | Subject Matter Experts | Jill Knowitall |
| Stakeholders | Billy Kidd, Jesse James |  |  |

| Project Details | Provide creative direction for a two-minute video that will feature the experience. This video will be featured in the next launch of the website on the home page. |
| --- | --- |
| Deliverables | Storyboards, final two-minute video in HD |
| Requirements | Create a two-minute video that speaks in an inviting voice and delivers inspiring music and visual design |
| Goals of the content | Increase awareness of the offering |
| Content Experience Requirements | Clearer messaging, more interactive content |
| Analytics & Metrics | Increased page views and time on page |
| Key Success Factors/Measurement Strategy | Increased signups |
| Business Objectives | The web presence will continue to position the client with a differentiated identity, educating and leading the market in the deluxe category for experienced and quality-focused travelers. |
| Consumer Objectives | Reach more of the HH1 150K+ market |
| Creative Objectives | Produce a best-in-class web experience that is significantly better than the client’s competitors’. |
| Target Audience | Boomers and matures (age 50+) who have the time, net worth and interest; HHI 150K+; experienced travelers; and those looking for a unique experience. |
| Legal Mandatories | All appropriate disclaimers |
| Project Timelines/Milestones | Friday 1/03: Video project kickoff Wed 1/08: Review draft Wed 1/08: Deliver brief and storyboard to client for approval Fri 1/10: Revise video storyboard and brief according to client feedback Mon 1/13: Review revised storyboard and voice-over script Tues 1/14 – Fri 1/17: Finalize storyboard Sat 1/25 – 1/31: Video shoot Mon 2/7 – Fri 2/11: Review video edits with client TBD: Final production including graphic assets and web-delivery artifacts |
| Messaging | Experience the impeccable details and personalized service unique to our client. |
| Competitive Landscape | While there are a number of competitors catering to HH1 150+, there is a lack of perceived value, which we hope to address. |
| Aesthetics (look and feel) | Key frames of the video sequence will show specific parts of the experience that the viewer (“our guest”) will experience as the video plays, while also leveraging photographic elements. Key images are supported with descriptive text and related transition scenes. |